CONTAINER FACILITY PLAN

Phase 1: Coworking + Café

Complete Land, Container, Layout & Construction Guide

MODULAR • EXPANDABLE • MODERN

January 2026

# QUICK SUMMARY

Phase 1 At-A-Glance

| Specification | Requirement |
| --- | --- |
| Land Size Needed | 3,000 - 4,000 sq ft (minimum) |
| Containers (Phase 1) | 4 units (40-foot containers) |
| Total Built Area | 1,280 sq ft (~119 sq m) |
| Coworking Capacity | 15-20 workstations |
| Café Seating | 15-20 seats |
| Investment | NPR 3.8M - 4.5M |
| Construction Time | 8-12 weeks |
| Expansion Ready | Yes - modular design |

What You Get in Phase 1

- Modern container-based structure

- 15-20 coworking stations (mix of hot desks, dedicated desks, cabins)

- Café with 15-20 seating capacity

- 1 meeting room (6-8 people)

- Reception area

- Restrooms (2)

- Outdoor seating/smoking area

- Parking for 8-10 bikes, 3-4 cars

- Full HVAC, WiFi, power backup

# SHIPPING CONTAINER BASICS

Shipping containers are the perfect building blocks for your space: strong, modular, quick to build, and 40-50% cheaper than traditional construction.

## Standard Container Sizes

| Type | Length | Width | Height | Internal Area | Price (Nepal) |
| --- | --- | --- | --- | --- | --- |
| 20-foot | 6.0 m | 2.4 m | 2.6 m | 14.4 sq m (155 sq ft) | NPR 200-300K |
| 40-foot | 12.0 m | 2.4 m | 2.6 m | 28.8 sq m (310 sq ft) | NPR 350-450K |
| 40-foot HC | 12.0 m | 2.4 m | 2.9 m | 28.8 sq m (310 sq ft) | NPR 400-500K |

Recommendation: Use 40-foot High Cube (HC) containers

High Cube gives you 2.9m ceiling height (vs 2.6m) which feels much more spacious and professional. The extra NPR 50K per container is worth it.

## Why Containers?

- Cost: 40-50% cheaper than brick construction

- Speed: 8-12 weeks vs 6-9 months

- Quality: Steel structure, weatherproof, durable

- Modular: Easy to expand by adding more containers

- Modern: Instagram-worthy, attracts young professionals

- Relocatable: Can move if lease ends (with effort)

- Sustainable: Upcycling, eco-friendly image

# PHASE 1: DETAILED LAYOUT

Phase 1 uses 4 containers arranged in an L-shape configuration. This creates an inviting courtyard feel with clear zones.

## Container Configuration

| Container | Size | Function | Area | Capacity |
| --- | --- | --- | --- | --- |
| Container 1 | 40ft HC | Coworking - Open Plan | 310 sq ft | 8 workstations |
| Container 2 | 40ft HC | Coworking - Cabins | 310 sq ft | 2 cabins (8 people) |
| Container 3 | 40ft HC | Café + Kitchen | 310 sq ft | 15-20 customers |
| Container 4 | 40ft HC | Meeting Room + Storage | 310 sq ft | 1 room (8 ppl) + storage |
| Additional | - | Restrooms (separate) | 40 sq ft | 2 units |

Total Built Area: 1,280 sq ft

## Detailed Zone Breakdown

### CONTAINER 1: Coworking Open Plan

- 3 Hot Desks (flexible seating)

- 5 Dedicated Desks (assigned seating)

- 1 Reception desk near entrance

- Small lounge area with 2 sofas

- Lockers for hot desk users

### CONTAINER 2: Private Cabins

- 2 Private Cabins (each 4 people)

- Glass partitions for natural light

- Each cabin: 4 desks, whiteboard, mini-fridge

- Soundproofing for privacy

- Perfect for small teams/startups

### CONTAINER 3: Café + Kitchen

- Front: Café seating for 15-20 people

- Counter with espresso machine, display fridge

- Back: Kitchen (microwave, sandwich press, prep area)

- Plumbing for sink and coffee station

- Can spill out to outdoor courtyard seating

### CONTAINER 4: Meeting Room + Storage

- Meeting room: 6-8 person capacity

- Conference table, TV/projector, whiteboard

- Soundproofed for calls and presentations

- Back section: Storage for supplies, inventory

- Server room (small, secure)

### RESTROOMS (Separate Structure)

- 2 full bathrooms (male/female)

- Modern fixtures, tiled

- Biogas or septic system

# LAND REQUIREMENTS

## Minimum Land Size

MINIMUM: 3,000 sq ft (80 ft × 40 ft)

RECOMMENDED: 3,500 - 4,000 sq ft (90 ft × 45 ft)

## Land Area Breakdown

| Zone | Area | Percentage |
| --- | --- | --- |
| 4 Containers (building footprint) | 1,280 sq ft | 32-43% |
| Outdoor courtyard/seating | 400 sq ft | 10-13% |
| Parking (8 bikes, 3 cars) | 800 sq ft | 20-27% |
| Walkways & circulation | 300 sq ft | 8-10% |
| Landscaping & buffer | 220 sq ft | 6-7% |
| Future expansion space | 500 sq ft | 13-17% |
| TOTAL RECOMMENDED | 3,500 sq ft | 100% |

Land Shape Preference

- Best: Rectangular (90 ft × 40-45 ft)

- Good: Square (60 ft × 60 ft)

- Avoid: Narrow/irregular shapes (hard to arrange containers)

- Road access: Minimum 12 ft wide (for container delivery)

## Land Location Criteria

- Zoning: Commercial use permitted

- Road access: Paved road, minimum 12 ft wide

- Ground: Relatively flat (max 5° slope)

- Drainage: No flood risk, good drainage

- Utilities: Water, 3-phase electricity available

- Internet: Fiber optic available (Worldlink/Vianet)

- Visibility: High visibility from main road is plus

## Lease Terms to Negotiate

- Duration: Minimum 5 years with renewal option

- Monthly rent: NPR 60,000 - 100,000 (depending on area)

- Deposit: 6-12 months (negotiate lower)

- Escalation: Maximum 10% per year

- Construction: Permission to install containers

- Removal: Clear terms on structure removal at lease end

# CONSTRUCTION PROCESS & TIMELINE

Total construction time: 8-12 weeks from container purchase to grand opening. Here's the detailed breakdown.

## Phase 1A: Site Preparation (Weeks 1-2)

Week 1: Site Work

- Clear and level the land

- Mark container positions

- Dig and pour concrete foundations (4 pads, 40×8 ft each)

- Create parking area base

- Cost: NPR 200,000-300,000

Week 2: Foundation Curing & Utilities

- Let concrete cure (5-7 days)

- Dig trenches for electrical, water, drainage

- Install main water line

- Install 3-phase electrical connection

- Cost: NPR 150,000-200,000

## Phase 1B: Container Delivery & Placement (Week 3)

- Purchase 4 containers (40ft HC)

- Crane delivery to site

- Placement on foundations

- Weld containers together at connection points

- Ensure level and stable

- Cost: NPR 1,800,000-2,000,000 (containers + delivery + crane)

## Phase 1C: Modification & Fit-Out (Weeks 4-7)

Week 4: Structural Modifications

- Cut openings for doors (8-10 doors)

- Cut openings for windows (12-15 windows)

- Reinforce cut sections

- Install door and window frames

- Cost: NPR 300,000-400,000

Week 5: Insulation & Interior Walls

- Spray foam insulation on walls and ceiling

- Install interior wall panels (plywood or gypsum)

- Build partition walls for cabins

- Install flooring (vinyl or laminate)

- Cost: NPR 400,000-500,000

Week 6: Electrical & HVAC

- Complete electrical wiring (outlets, switches, lights)

- Install 6-8 split AC units

- Install LED lighting throughout

- Install ceiling fans

- Cost: NPR 400,000-500,000

Week 7: Plumbing & Kitchen

- Install plumbing for kitchen and restrooms

- Build restroom units (separate structure)

- Install sinks, toilets, fixtures

- Set up water purification system

- Cost: NPR 200,000-300,000

## Phase 1D: Finishing & Setup (Weeks 8-10)

Week 8: Interior Finishing

- Paint all interior walls

- Install doors and windows

- Install glass partitions for cabins

- Install blinds/curtains

- Cost: NPR 200,000-250,000

Week 9: Furniture & Equipment

- Deliver and install all coworking furniture

- Set up café seating and tables

- Install café equipment (espresso machine, etc)

- Set up meeting room (table, TV, whiteboard)

- Cost: NPR 900,000 (from pre-sales)

Week 10: IT & Final Touches

- Install WiFi routers and network equipment

- Set up CCTV system

- Install generator

- Landscaping and signage

- Deep cleaning

- Cost: NPR 350,000

## Phase 1E: Testing & Launch (Weeks 11-12)

- Test all systems (HVAC, WiFi, plumbing, electrical)

- Staff training

- Soft opening for founding members

- Gather feedback and make adjustments

- GRAND OPENING!

# PHASE 1 INVESTMENT BREAKDOWN

| Item | Cost (NPR) | Notes |
| --- | --- | --- |
| Land Lease (6mo deposit) | 480,000 | @ 80K/month |
| Site Preparation | 500,000 | Foundations, utilities |
| 4 Containers (40ft HC) | 1,800,000 | Including delivery |
| Modifications | 400,000 | Doors, windows, cuts |
| Insulation & Interior | 500,000 | Walls, floors, ceiling |
| Electrical & HVAC | 500,000 | Wiring, ACs, lighting |
| Plumbing & Restrooms | 300,000 | Kitchen, toilets |
| Interior Finishing | 250,000 | Paint, fixtures |
| IT & Security | 350,000 | WiFi, CCTV, generator |
| Landscaping & Signage | 100,000 | Exterior |
| SUBTOTAL | 5,180,000 |  |
| Furniture & Equipment | 900,000 | From pre-sales |
| Working Capital | 800,000 | 3-4 months buffer |
| GRAND TOTAL | 6,880,000 | Complete ready-to-open |

MINUS Pre-Sales: NPR 1,200,000

NET INVESTMENT NEEDED: NPR 5,680,000

Funding Split:

• You: NPR 2,840,000 (50%)

• Investors: NPR 2,840,000 (50%)

# EXPANSION MODULES (Future Phases)

The beauty of container design: you can expand by simply adding more containers. Here's how each future phase looks.

## Phase 2: Expanded Café/Coworking

Add 2 containers:

- Container 5: Additional coworking (10 more desks)

- Container 6: Expanded café seating

- Total added: 620 sq ft

- Investment: NPR 2,500,000

- Timeline: 4-6 weeks

## Phase 3: Sports Viewing Area

Add 2 containers:

- Container 7-8: Sports lounge with 4 large screens

- Bar counter

- Seating for 30-40 people

- Total added: 620 sq ft

- Investment: NPR 2,800,000

- Timeline: 6-8 weeks

## Phase 4: Full Restaurant Kitchen

Add 1-2 containers:

- Container 9: Commercial kitchen

- Container 10 (optional): Staff room/storage

- Full cooking equipment

- Total added: 310-620 sq ft

- Investment: NPR 3,000,000

- Timeline: 8 weeks

Maximum Capacity: 10-12 containers on 4,000 sq ft land

# KEY CONTRACTORS & SUPPLIERS (NEPAL)

## Container Suppliers

| Company | Contact | Services |
| --- | --- | --- |
| Nepal Container Trading | Balaju, Kathmandu | New & used containers |
| Everest Container Depot | Balkhu, Kathmandu | Sales & modification |
| Container Nepal | Tripureshwor | Custom container buildings |
| Online Search | Facebook/Hamrobazaar | Many small suppliers |

Tip: Negotiate! Container prices vary widely. Get 3-4 quotes.

## Construction/Modification

- Local fabricators/welders: Check Thapathali, Balaju industrial areas

- Architecture firms: Several now specialize in container projects

- Get detailed quotes including cutting, welding, insulation, interior

## Furniture (Already Researched)

- KursiNepal.com - Office furniture

- SB Furniture - Lounge & café furniture

- Hamrobazaar - Budget options

## Café Equipment

- Kitchen Craft Nepal - Complete kitchen equipment

- Classy Kitchen Equipment - Commercial appliances

- Local suppliers in New Road/Ason area

# CRITICAL SUCCESS FACTORS

### 1. Location is 80% of Success

Don't cheap out on land location. NPR 80K/month in a great location beats NPR 50K/month in a bad one. Target: Battisputali, New Baneshwor, or Pulchowk areas.

### 2. Insulation is Essential

Steel containers get HOT in Kathmandu summer. Budget properly for spray foam insulation. This isn't optional - it's essential for comfort and AC efficiency.

### 3. Choose Your Container Modifier Carefully

Get 3-4 quotes for modification work. Visit their previous projects. Check welding quality - bad welding = leaks and structural issues. Don't go with cheapest, go with proven.

### 4. Build in the Dry Season

Plan construction for October-April (dry season). Monsoon construction is slower and more expensive. Foundations need to cure properly.

### 5. Get All Permits First

Ward office permits, food service license, fire safety clearance. Do this BEFORE starting construction. Fines and delays are costly.

### 6. Overbudget by 20%

Container projects always have surprises. Budget NPR 5.7M but have NPR 6.8M available. The extra 20% buffer will save you stress.

### 7. Phase It Right

Start with Phase 1 (4 containers). Prove the concept. Only expand when you have 85%+ occupancy and waiting lists. Don't overbuild.

---

This is your complete container facility blueprint.

Land: 3,500 sq ft • Containers: 4 units • Timeline: 8-12 weeks

Investment: NPR 5.7M • Capacity: 15-20 coworkers + 20 café customers

Modern • Modular • Expandable • Ready to Build! 🚀

January 2026